## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
| US1 | user | Register if you are new user | I Can Receive A Confirmation/Verification Mail
1 | US2 | user | Receive A Confirmation Mail | I Can Access application of cloud
1 | US3 | user | Login Into The System Using my email id And Password | I Can View/Edit My Profile
1 | SB1/US4 | user | Access my workspace | I can keep track of my work done till time
1 | SB1/US5 | user | Go to the home page | I Can track all the happenings
1 | US6 | user | Modify The Account Password | I Can Keep My Account Secure
1 | SB1/US7 | user | Go to the save option | I can access all my saved data
1 | SB1/US8 | user | Share Among Other users | I Can Share My data
1 | SB1/US9 | user | Save the data | I Can save my data
1 | US19 | user | View My mails | I Can Keep A Check On My Activities
1 | US11 | user | Download files | I Can download my files from the internet
1 | US12 | user | Mark important | I Can Manage My Attendance
1 | US13 | user | See The dowloading Status | I Can see The progress in downloading
1 | US14 | user | See my updates | I can use all the
1 | US15 | user | backe up data | I can have a backup of my data
1 | US16 | user | host website | I can host websites of my choice
1 | US17 | user | host blogs | I can host different blogs form my account
1 | US18 | user | stream audios | I can stream audios
1 | US19 | user | stream videos | I can stream videos
2 | SB2/US20 | user | SAAS | I can use different softwares for the develpoement
2 | SB2/US20 | user | PAAS | I can deploy my project
2 | SB2/US22 | user | STAAS | I can use different infrastructure for project development
2 | SB2/US23 | DBA | Fire Insert Queries | I Can Insert New Records In The Database
2 | SB2/US24 | DBA | Fire Select Queries | I Can View The Records
3 | SB3/US25 | DBA | Fire Update Queries | I Can Keep The Database Updated
3 | SB3/US26 | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data
3 | US27 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
3 | US28 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
2 | US29 | CV | Deliver Software | I can provide my cient with different softwares
2 | US30 | CV | SAAS | I can provide my client softwares for project development
2 | US31 | CV | PAAS | I can provide my client platform to deploy the project
3 | US32 | CV | IAAS | I can provide my client infrastructure to develop the project
3 | US33 | CV | Provide Memory | I can provide my client memory to store their data
4 | US20 | user | signup with the gmailid. | I can signup with the account
4 | US21 | user | Sign up authentication | I can signup with security
4 | US22 | user | sign in with gmail and password | I can log in with gmail id and password.
4 | US23 | user | update the password | I can updtae the password.
4 | US24 | user | forgot password | I can forget the password so I can change it.
4 | US25 | user | delete the account | I can delete my account
5 | SB3/US27 | Admin | Managing all the sign's up done by the user | Admin have a record of all the sign's up done by the user
5 | SB3/US28 | Admin | Managing all the login's done by the user | Admin have a record of all the login's done by the user
5 | SB3/US29 | Admin | Manages the database for the logined users | Admin can manage the data
5 | SB3/US30 | Admin | Manage the forget password option for the users | Admin can manage the forget password option
5 | SB3/US31 | Admin | Sends a confirmation mail when a user sign's up | Admin can send a confirmation mail when any user sign's up
5 | SB3/US32 | Admin | Won't let a user to login until he confirms the signed up login id | Admin will check for that the user has confirmed the email id or not
5 | SB3/US33 | Admin | Check the number users online on the website | Admin can check the number users online
5 | SB3/US34 | Admin | Check the number of hits on the website | Admin can check the number of hits
5 | SB3/US35 | Admin | Manage the password options | Admin can manage password options
5 | SB3/US36 | Admin | Manage the inventory panel for the website | Admin can manage the inventory panel for the website
5 | SB3/US37 | Admin | All the comments will be coming to the Admin panel | Admin should check all the comments added by the users
5 | SB3/US38 | Admin | All the queries asked by the users needs to be managed by the Admin | Admin can check and manage all the queries
5 | SB3/US39 | Admin | All the queries needs to be answered through the Admin Panel | Admin needs to answer all the queries
5 | SB3/US40 | Admin | All the answers to the queries will reach the user through email | Admin should answer the query of any user through email
5 | SB3/US41 | Admin | Can check and edit anything in the comments section | Admin can check and edit any comment
5 | SB3/US42 | Admin | Can manage the interface given for the users | Admin can manage the interface of the website
5 | SB3/US43 | Admin | Cares for the site | Admin can take care of the website
5 | SB3/US44 | Admin | Can add and delete any item on the website | Admin can add and delete any item on the website
5 | SB3/US45 | Admin | Contact section will be managed by the Admin Panel | Admin can manage the contact sectionon the website
5 | SB3/US46 | Admin | Can add new developers which are helping the Admin team | Admin can add new developers
5 | SB3/US47 | Admin | Meet the team panel needs to be managed by the Admin | Admin can manage meet the team panel on the website
5 | SB3/US48 | Admin | Security of the website | Admin can control the security of the website
5 | SB3/US49 | Admin | Supports the forget password option | Admin can support the forget password option
4 | US26 | User | Can Sign Up if new to the website | User can sign up if new on the website
4 | US27 | User | Should provide with the correct personal information to sign up | User should provide with the correct personal information
4 | US28 | User | Should confirm the email ID from the confirmation email sent | User should confirm the email id through the confirmation mail
4 | US29 | User | Now the new user can check all the products present on the website | User can check all the products present on the website
4 | US30 | User | Can login if is a existing user | User can login if is an existing user
4 | US31 | User | FAQ will help the users to get answers to there questions easily | User will get the answers to their queries through FAQ section easily
4 | US32 | User | Users can ask questions in the FAQ sections | User can ask questions in FAQ section as well
4 | US33 | User | User can use the contact us option to ask for any query | User can use the contact us option to ask for any query
4 | US34 | User | User can change their personal information | User can change their personal information
4 | US35 | User | User can change their mobile number | User can change their mobile number
4 | SB3/US50 | Admin | Check if there are more than one active seession of a user | Admin can check if there are more than one active seession of a user
5 | SB3/US51 | Admin | Delete the suspicious accounts | Admin can delete any suspicious account
5 | SB3/US52 | Admin | Delete accounts of users who post false information | Admin can delete accounts of users who post false information
4

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Legal Aid>
SB1/US4 | Access my workspace | SB1/D1/T1
SB1/D1/T2
SB1/D1/T3
SB1/D1/T4
SB1/D1/T5
SB1/D1/T6
SB1/US5 | Go to the home page | SB1/D2/T1
SB1/D2/T2
SB1/D2/T3
SB1/D2/T4
SB1/D2/T5
SB1/US7 | Go to the save option | SB1/D3/T1
SB1/D3/T2
SB1/D3/T3
SB1/D3/T4
SB1/US8 | Share Among Other users | SB1/D4/T1
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB1/D4/T5
SB1/US9 | Save the data | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| YK | Yash Katta
| RD | Rashi Dixit
| MS | Manisha Singh
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
US22 | STAAS | SB2/D1/T1 | Designing the GUI | RD
|  | SB2/D1/T2 | Connection with database to fetch the data | MS
|  | SB2/D1/T3 | Backend of the module on localhost and then on server. | YK
US20 | SAAS | SB2/D2/T1 | Designing of GUI | RD
|  | SB2/D2/T2 | Validating user input at client level | YK
|  | SB2/D2/T3 | Validating user input at server level | YK
|  | SB2/D2/T4 | Connection with Docker Database to insert the record. | YK+MS
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RD
US23 | Fire Insert Queries | SB2/D3/T1 | write sql queries | RD
|  | SB2/D3/T2 | validate sql queries | RD
|  | SB2/D3/T3 | Connection with database to update the status in the database. | YK
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | YK+RD+MS
US24 | Fire Select Queries | SB2/D4/T1 | writing sql queries | RD
|  | SB2/D4/T2 | validating sql queries | RD
|  | SB2/D4/T3 | Connection with Database to insert the record. | YK
|  | SB2/D4/T4 | Testing of the module on localhost and then on server. | RD+YK+MS

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Legal AID>
US26 | Fire Delete Queries |  | write sql queries | RD
|  |  | validate sql queries | RD
|  |  | Connection with database to update the status in the database. | YK
|  |  | Testing of the module on localhost and then on server. | YK+RD+MS
US25 | Fire Update Queries |  | write sql queries | RD
|  |  | validate sql queries | RD
|  |  | Connection with database to update the status in the database. | YK
|  |  | Testing of the module on localhost and then on server. | YK+RD+MS

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Legal Aid >

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days